## Team1_Estimated_Effort
Task Name: (Dependencies top to bott | [8 empty] | Jared | John | Kody | Sam | Novin | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 0 |  | 0
|  | Design architecture | Project Manager | [10 empty] | 0
| Requirements |  |  |  |  | 0.75 |  | 0 | [5 empty] | 0
|  | Gather | Requirements Engineer | All Hands | 0.25 | [8 empty] | 0
|  | Analyze | Requirements Engineer | All Hands | 0.25 | [8 empty] | 0
|  | Specify | Requirements Engineer | All Hands | 0.25 | [8 empty] | 0
| Documentation |  |  |  |  | 6 |  | 0 | [5 empty] | 0
|  | Project Charter | Project Manager | Kody | 1 | [8 empty] | 0
|  | Release Plan | Project Manager | Jared | 0.5 | [8 empty] | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Jared, John, Kody, Sam, Novin | 1.25 | [8 empty] | 0
|  | Project Plan | Project Manager, Developers | Jared, John, Kody, Sam, Novin | 1 | [8 empty] | 0
|  | Architecture Document | Architect | Jared, John, Kody, Sam, Novin | 1.25 | [8 empty] | 0
|  | Test Report | Tester | Jared, John, Kody, Sam, Novin | 0.5 | [8 empty] | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Jared, John, Kody, Sam, Novin | 0.5 | [8 empty] | 0
Coding | [13 empty] | 0
Iteration 1: | Development |  |  |  |  | 12.5 |  | 0 | [5 empty] | 0
|  | Determine technology needs | Developer | Jared | 2 | [8 empty] | 0
|  | Research and learn new language and environment | Developer | Kody,Novin | 1 | [8 empty] | 0
|  | Set up proxy server software | Developer | Sam | 1.5 | [8 empty] | 0
|  | Write basic proxy code | Developer | Sam | 1.5 | [8 empty] | 0
|  | Create and repurpose MVC .Net VS Project | Developer | John, Jared | 0.5 | [8 empty] | 0
|  | Create web site design mock ups | Developer | John, Kody | 1
|  | Create site map | Developer | John, Kody | 2 | [8 empty] | 0
|  | Write code for managing HTTP session | Developer | Kody,Novin | 1.5 | [8 empty] | 0
|  | Unit Testing | Developer | Jared | 1.5 | [8 empty] | 0
| Analysis |  |  |  |  | 3 |  | 0 | [5 empty] | 0
|  | System Testing | Tester | [10 empty] | 0
|  | Bug fix as required | Tester, Developer | Jared, Kody | 1 | [8 empty] | 0
|  | Evaluate needs for next iteration | Project Manager | Jared | 2 | [8 empty] | 0
Iteration 2: | Design |  |  |  |  | 0 |  | 0 | [5 empty] | 0
0
0
0
0
0
| Development |  |  |  |  | 0 |  | 0 | [5 empty] | 0
0
0
0
0
0
| Analysis |  |  |  |  | 0 |  | 0 | [5 empty] | 0
0
0
0
Iteration 3: | Design |  |  |  |  | 0 |  | 0 | [5 empty] | 0
0
0
0
0
| Development |  |  |  |  | 0 |  | 0 | [5 empty] | 0
0
0
0
0
0
| Analysis |  |  |  |  | 0 |  | 0 | [5 empty] | 0
0
0
Total |  |  |  |  | 22.25 | 22.25 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0